## Fliden
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Fliden | 7 | 6 | 1 | 0 - Reading about YII framework 1 - Review the requiremnts and features discussed in meeting 5 - Plan next meeting, communicate dates and tasks with the team 6 - Set up working environtment, install Netbeand, set up git, install XAMPP | 1 | 1 | 0 | 0 | 0 | 2 | 2 | - Complete Requirements Document - Plan next meeting - Write use stories in Pivotal tracker - Prepare presentation - Communicate with team to make sure we address all the weekly group tasks - Read more about YII framework | 10
2 | Fliden | 8 | 7 | 1 | 1 - Write user stories 1 - Write SPMP 5 - Plan next phase and iteration 5 - Plan next meeting, communicate dates and tasks with the team 6 - Write presentation bullets | 0 | 4 | 0 | 0 | 0 | 2 | 1 | - Complete Requirements Document with Risk Management - Review initial database design - Review YII framework, use it to create CRUD database operations - Try and implement YII MVC structure (create initial prototype) - Plan next meeting | 10

## Fyodor
week | Total time spent working this week (h) | Work time spent individually | Total meeting time | Time Spent on individual task (hrs) | [6 empty] | Estimated tasks for next week | Total estimated time
|  |  |  | Learning | Requirement Analysis | design | implementation | test | communication / management | unclassified
1 | 5 | 4 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 3 | 5
2 | 3.5 | 3.5 | 0 | 0 | 1 | 1 | 0.5 | 0 | 1 | 0 | 4 | 5
3 | 0 | 0
4 | 0 | 0
5 | 0 | 0
6 | 0 | 0
7 | 0 | 0
8 | 0 | 0
9 | 0 | 0
10 | 0 | 0
11 | 0 | 0
12 | 0 | 0
Note on G2: Read through the document Beth sent around and provided feedback.
Note on I2: Configured Github repo for the team and added the yii bootstrap for quick and easy startup
Note on K2: wrote up a brief tutorial on how to get set up with Github and the project that has been commited.
Note on L2: Helped Beth configure her WAMP installation.
Note on G3: Read through requirements and made sure things are correct.
Note on H3: Created a ERM to double check team logic on FK use and inheritense
Note on I3: Updated Documentation. Filed issue with ignore file.
Note on K3: Talked about ERM that Beth sent around. Adding professor to Github and email/username resolution.

## Chih-Chi
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Chih-Chi | 5 | 4 | 1 | 0 - Setup and learn Github 0 - Read on Yii frame work 0 - Install wamp server | 4 | [6 empty] | Add user story on PivotalTracker Make sure Github is working Help complete our SPMP document Read more on Yii framework | 6
2 | Chih-Chi | 6 | 5 | 1 | 2 - add user storys on PivitalTracker 0 - Git tutorial lesson 0 - Read through SPMP document 0 - Make a commit on GitHub | 4 |  | 1 |  |  |  |  | Work on login and registor page Read more on Yii framework Understand and provide feedback to our database design | 8
3 | Chih-Chi | 0 | 0
4 | Chih-Chi | 0 | 0
5 | Chih-Chi | 0 | 0
6 | Chih-Chi | 0 | 0
7 | Chih-Chi | 0 | 0
8 | Chih-Chi | 0 | 0

## Gloria
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Gloria | 4 | 4 | 1 | 0 - Learn GitHub & Yii Framework 0 - Set up Tools | 4 | [6 empty] | 1 - Write User Stories, 1 - Review Requirements Doc, 2 - Design project logo, 2 - Start Wireframes, 6 - Create presentation doc for Group Presentation | 8
2 | Gloria | 8 | 8 | 1 | 1 - Write User Stories, 1 - Review Requirements Doc, 2 - Design project logo, 2 - Create user flow, 6 - Create presentation doc for Group Presentation |  | 2 | 4 |  |  |  | 2 | 2 - Wireframes | 6

## Beth
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Beth | 6 | 6 | 1 | 0 - Learned tools, researched similar projects online 1 - Created system requirements based on discussions; updated SPMP | 2 | 3 | [5 empty] | Revise SPMP, help prepare for presentation, get more familiar with tools, create user stories for pivotaltracker | 10 hrs
2 | Beth | 8 | 8 | 1 | 1 - Wrote user stories, incorporated all user stories into requirements design in SPMP 2 - Created preliminary database design | 0 | 3 | 4 |  |  |  |  | Revise SPMP, learn how to create database in Yii, update SPMP with non-functional requirements

## Imaad
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Imaad | 5 | 4 | 1 | 0 - Installing github and MAMP server 0 - git and yii tutorials | 4 | [6 empty] | 1. Add Use cases 2. Empty commit on git 3. Work on the SPMP document 4. Learn yii framework | 7

## Samuel
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Samuel | 5 | 5 | 1 | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion 5 - communication / management | 3 | 1 |  |  |  | 1 |  | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion & documentation 5 - communication / management

## Chao-Te
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Chao-Te | 5 | 4 | 1 | 0 - Setup github and XAMPP server 0 - Review and learn PHP | 4 | [6 empty] | Learn more about YII framework and php Learn more about Git Create user stories | 8