## Fliden
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Fliden | 7 | 6 | 1 | 0 - Reading about YII framework 1 - Review the requiremnts and features discussed in meeting 5 - Plan next meeting, communicate dates and tasks with the team 6 - Set up working environtment, install Netbeand, set up git, install XAMPP | 1 | 1 | 0 | 0 | 0 | 2 | 2 | - Complete Requirements Document - Plan next meeting - Write use stories in Pivotal tracker - Prepare presentation - Communicate with team to make sure we address all the weekly group tasks - Read more about YII framework | 10
2 | Fliden | 8 | 7 | 1 | 1 - Write user stories 1 - Write SPMP 5 - Plan next phase and iteration 5 - Plan next meeting, communicate dates and tasks with the team 6 - Write presentation bullets | 0 | 4 | 0 | 0 | 0 | 2 | 1 | - Complete Requirements Document with Risk Management - Review initial database design - Review YII framework, use it to create CRUD database operations - Try and implement YII MVC structure (create initial prototype) - Plan next meeting | 10
3 | Fliden | 9 | 8 | 1 | 0 - Lear and try Gii tool to generate code. 0 - Learn more about YII MVC structure 1 - Complete Requirements Document with Risk Management 1 - Pivotal Tracker update user stories and organization 2 - Review initial database design 3 - Set up and try the Yii db migration 5 - Plan next meeting and next week | 3 | 2 | 1 | 1 | 0 | 1 | 0 | - Address notes on SPMP - Pivotal Tracker: Add different tasks to user stories - Pivotal Tracker: Add UI to them etc - Pivotal Tracker: Split stories in smaller ones - Run Gii on all db tables to generate CRUD code - program create survey page and its related code and classes | 10
4 | Fliden | 8 | 7 | 1 | 1 - Update SPMP document 3 - Create CRUD operations for each db table 3 - Start programing create survey pages and its related classes and code 4 - Update Pivotal Tracker: add tasks, add/change person responsible for each task 4 - Communicate with the team 4 - Help other team members with version control/Yii framework | 0 | 1 | 0 | 5 | 0 | 1 | 0 | - Finish survey create page and its related code - Prepare and coordinate for next weeks presentation - Cooperate with Fyodor with certain changes to the code (remove user levels, add survey title field) - Cooperate with Gloria and Beth on the class diagram - try to create a few unit tests | 10
5 | Fliden | 15 | 14 | 1 | 3 - Finished survey create page and its related code 3 - Cooperate with Fyodor with certain changes to the code (remove user levels, add survey title field) 5 - Prepare and coordinate for next weeks presentation 5 - Help the team fix version control issues and Yii framework issues 5 - Plan next iteration/Add user stories/Change user story evaluations | 0 | 0 | 0 | 10 | 0 | 4 | 0 | - Coding of different type of questions - Write unit tests - Research phpdoc and plan documentation | 7
6 | Fliden | 5 | 4 | 0 | 1 - research phpdoc 3 - started coding of different type of questions 3 - write unit tests fpr remaining modules 3 - start writting docblocks | 1 | 0 | 0 | 4 | 0 | 0 | 0 | - finish writting phpdocs - continue coding different types of questions - plan next meeting and plan next presentation - finish and write report on unit testing - fix different bugs | 10
7 | Fliden | 6 | 5 | 1 | 3 - wrote phpdocs 3 - continued coding different types of questions 5 - plan next meeting and plan next presentation | 0 | 0 | 0 | 3 | 0 | 2 | 0 | - write unit tests and write simple report on unit testing to discuss it with the group and Chao-Te who is going to present about testing next week - write docblocks and work with Beth to set up and generate the initial documentation - continue coding different types of questions - write project management part of the next presentation - gather all the information from the team and put together the next presentation - plan next meeting - start sending daily status updates email | 12
8 | Fliden | 12 | 11 | 1 | 4 - write unit tests and write simple report on unit testing to discuss it with the group and Chao-Te who is going to present about testing next week 5 - write project management part of the next presentation 5 - gather all the information from the team and put together the next presentation 5 - plan next meeting 5 - start sending daily status updates email | 0 | 0 | 0 | 0 | 4 | 7 | 0 | - go through Pivotal Tracker stories, update stories, split a few of them in smaller stories and reastimate for iteration 3 - Go thourgh the latest version of the code in master branch and add any remaining tasks or bugs in GitHub for the existing functionality - go through GitHub tasks and bugs and fix as many as possible - help with SDD document - run phpdoc(or a comparable alternative) to get the current documentation. Maybe add some more docs as well - plan next meeting and communicate plan with the group | 10
9 | Fliden | 8 | 7 | 1 | 3 - Went thourgh the latest version of the code in master branch and added any remaining tasks or bugs in GitHub for the existing functionality 3 - Went through GitHub and closed a few bugs 3 - Run PhpDocumentor to get the current documentation. Added some more docs as well. I also did some refactoring of the code and changes to make the class hierarchy play better with PhpDocumentor 5 - Went through Pivotal Tracker stories, updated stories and reastimated for iteration 3 5 - Help with SDD document 5 - Plan next meeting and communicate plan with the group | 0 | 0 | 0 | 4 | 0 | 3 | 0 | - create the architecture diagram for the SDD - fix bugs from GitHub - help with the implementation of survey taker part - plan next meeting and communicate plan with the group | 7
10 | Fliden | 8 | 7 | 1 | 1 - go through the SDD document 3 - fix bugs from GitHub 3 - help with the implementation of survey taker part, edit only unpublished surveys, regenerate hash when unpublishing 3 - merged everything to master and fix the conflicts 3 - went through and reviewed all the latest code 5 - plan next meeting and communicate plan with the group | 0 | 1 | 0 | 5 | 0 | 1 | 0 | - fix the survey versioning, add preview to the published surveys and resolve the hash vs id issue - work on the implementation of the survey report part. Focus on short answer questions and the "word counter" section to generate list of most used words. - re-generate documentation with PhpDocumentor and check the structure of the docs and make any needed changes - work on deploying the project - plan for the final presentation - send reminders to the group about everybody's tasks to get ready for the final demo and presentation | 10

## Fyodor
week | Total time spent working this week (h) | Work time spent individually | Total meeting time | Time Spent on individual task (hrs) | [6 empty] | Estimated tasks for next week | Total estimated time
|  |  |  | Learning | Requirement Analysis | design | implementation | test | communication / management | unclassified
1 | 5 | 4 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 3 | 5
2 | 3.5 | 3.5 | 0 | 0 | 1 | 1 | 0.5 | 0 | 1 | 0 | 4 | 5
3 | 9 | 8 | 1 | 1 | 0 | 0 | 5 | 0 | 1 | 1 | 6 | 8
4 | 9 | 8 | 1 | 0 | 0 | 2 | 3 | 1 | 2 | 0 | 7 | 9
5 | 9 | 8 | 1 | 1 | 0 | 1 | 3 | 0 | 2 | 1 | 6 | 8
6 | 8 | 7 | 1 | 0 | 0 | 1 | 4 | 0 | 2 | 0 | 8 | 9
7 | 10 | 9 | 1 | 0 | 1 | 1 | 4 | 1 | 2 | 0 | 8 | 10
8 | 10 | 9 | 1 | 0 | 0 | 1 | 5 | 1 | 2 | 0 | 7 | 8
9 | 8 | 7 | 1 | 1 | 1 | 0 | 2 | 2 | 1 | 0 | 7 | 8
10 | 9 | 8 | 1 | 1 | 0 | 0 | 4 | 1 | 1 | 1
11 | 0 | 0
12 | 0 | 0
Note on G2: Read through the document Beth sent around and provided feedback.
Note on I2: Configured Github repo for the team and added the yii bootstrap for quick and easy startup
Note on K2: wrote up a brief tutorial on how to get set up with Github and the project that has been commited.
Note on L2: Helped Beth configure her WAMP installation.
Note on G3: Read through requirements and made sure things are correct.
Note on H3: Created a ERM to double check team logic on FK use and inheritense
Note on I3: Updated Documentation. Filed issue with ignore file.
Note on K3: Talked about ERM that Beth sent around. Adding professor to Github and email/username resolution.
Note on F4: migration review.
Note on I4: * Moved the config passwords outside the config file. * Themes set up to be used. * Ignored environment specific configuration files. * Removed redundant layout * Created parent Model class* * Added survey_creater table to database migration * Generated survey_creator model * Authentication is done against the database test user.
Note on K4: helping set up and explaining migrations and how to use yiic to run them.
Note on L4: Helped beth configure her MySQL database.
Note on H5: Worked on Gloria's design and integrated it with master..
Note on I5: * Worked on CRUD operations and fixed up the * Authentication/Registration module. * Issue fixes.
Note on J5: Manual navigation and authentication/registration work properly.
Note on K5: * Emailing group of major updates. * Pivitol tracker finishing tasks. * Video chat with Gloria to set up her MAMP
Note on F6: figuring out how to remove FK'd column in a migration. 1)remove FK, 2)remove index, 3) remove column.
Note on I6: * Commenting * Cleaning up code & removing uneeded files. * Minor Design fixes * Bug fixes * Migration additions.
Note on K6: * Communicated with Dloria about design specifics and how to accomplish some tasks. * Taught team members how to work with Yii. * Discussed with Beth various strategies on how to clean up the schema.
Note on L6: code review.
Note on H7: styles the draggable questions so they can be ordered.
Note on I7: Questions are now sortable for a survey.
Note on K7: updating issues on Github. Assigning issue on Github Reviewing code.
Note on G8: Reading through documentation making sure I'm implementing the proper thing and checking what's in/out of scope
Note on H8: Designing the rough layout of all the items on the screen.
Note on I8: Adding functionality to edit, add and delete questions.
Note on J8: making sure that sorting is persisted to the database and is reflected properly on the ui.
Note on K8: communicated with the group and Glorioa specificly on how to implement certain things from the UX perspective.
Note on H9: Reworking how answer choice selection changes behavior of the question.
Note on I9: Unified the Survey form. Adding questions/answers along with sorting and figuring out when to prevent adding more questions.
Note on J9: Making sure things worked properly. Tested and found bugs / fixed them.
Note on K9: Talked to Gloria and the rest of the team about what sort of User experience is desired.
Note on F10: Figuring out how to properly generate a hash
Note on I10: * Created a strategy patter when different types of questions are added to the survey update for. * Made the model return state specific values to the view.
Note on J10: made sure debug and test my code from this and last week.
Note on K10: communicated with team about current tasks they are one, and how to make them work.
Note on F11: Researching how to deploy yii Projects
Note on I11: 1. Added confirmation modal to unpublish & delete survey actions. 2.Commented code & added documentation. 3. bug/issue fixes.
Note on J11: testing my issue resolutions.
Note on K11: Feedback to survey take implementation.
Note on L11: Added SSD documentation.

## Chih-Chi
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Chih-Chi | 5 | 4 | 1 | 0 - Setup and learn Github 0 - Read on Yii frame work 0 - Install wamp server | 4 | [6 empty] | Add user story on PivotalTracker Make sure Github is working Help complete our SPMP document Read more on Yii framework | 6
2 | Chih-Chi | 6 | 5 | 1 | 2 - add user storys on PivitalTracker 0 - Git tutorial lesson 0 - Read through SPMP document 0 - Make a commit on GitHub | 4 |  | 1 |  |  |  |  | Work on login and registor page Read more on Yii framework Understand and provide feedback to our database design | 8
3 | Chih-Chi | 9 | 8 | 1 | 3 - Login page and integrating 3 - Yii database migration |  |  |  | 8 |  |  |  | Port login page to Yii framework | 10
4 | Chih-Chi | 11 | 10 | 1 | 3 - Login/Register page and Yii framework intergration |  |  |  | 10 |  |  |  | Prepare for next weeks report Unit testing | 6
5 | Chih-Chi | 6.5 | 5.5 | 1 | 0 - learning phpunit and unit testing 3 - unit test case for survey creator model 6 - presentation preparation | 4 |  |  | 1 |  |  | 0.5 | Help with implementing more survey question types More unit testing Learn php doc | 9
6 | Chih-Chi | 6 | 5 | 1 | 0 - learning php documentor | 5 | [6 empty] | Help with implementing more survey question types | 6
7 | Chih-Chi | 7 | 6 | 1 | 3 - Partial multiple choice implementation 0 - More learning on YII | 1.5 |  |  | 4.5 |  |  |  | Help with implementing more survey question types Account setting page | 8
8 | Chih-Chi | 8 | 7 | 1 | 3 - Account setting page 3 - Made changes to multiple choice |  |  |  | 7 |  |  |  | Add more question types Help with take survey page | 8
9 | Chih-Chi | 7 | 6 | 1 | 3 - Worked on take survey page |  |  |  | 6 |  |  |  | Continue to work on take survey page | 8
10 | Chih-Chi | 7 | 6 | 1 | 3 - Complete take survey page |  |  |  | 6 |  |  |  | Help with report page Presentation notes | 8

## Gloria
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Gloria | 5 | 4 | 1 | 0 - Learn GitHub & Yii Framework 0 - Set up Tools | 4 | [6 empty] | 1 - Write User Stories, 1 - Review Requirements Doc, 2 - Design project logo, 2 - Start Wireframes, 6 - Create presentation doc for Group Presentation | 8
2 | Gloria | 9 | 8 | 1 | 1 - Write User Stories, 1 - Review Requirements Doc, 2 - Design project logo, 2 - Create user flow, 6 - Create presentation doc for Group Presentation |  | 2 | 4 |  |  |  | 2 | 2 - Wireframes | 6
3 | Gloria | 8 | 7 | 1 | 2 - Wireframes, 2 - Class Diagram |  |  | 7 |  |  |  |  | 0 - Learn & set up Yii, 3 - CSS, 2 - Wireframes | 7
4 | Gloria | 11 | 10 | 1 | 1 - Update SPMP doc based on feedback, 1 - add new User Story, 2 - Add wireframes to Pivotal Tracker, 0 - Learn Yii, 0 - Set up local database, 3 - Homepage, Survey & Survey Editor pages UI (PHP & CSS) | 4 | 1 | 1 | 4 |  |  |  | 3 - Finish UI for iteration #1, 2 - Work on look & feel, 6 - Presentation deck for Group Presentation | 8
5 | Gloria | 12 | 11 | 1 | 2 - Work on look & feel, 3 - Finish UI for iteration #1, 6 - Presentation deck for Group Presentation |  |  | 1 | 6 |  |  | 4 | 6 - PHP Documentation, 3 - Continue working on UI, 3 - Adding more questions | 5
6 | Gloria | 5 | 4 | 1 | 3 - UI for adding more question types, 6 - PHP Documentation |  |  |  | 3 |  |  | 1 | 6 - PHP Documentation, 2 - UI Wireframes, 3 - Fix UX bugs, 3 - continue work on UI / CSS | 7
7 | Gloria | 7 | 6 | 1 | 6 - PHP Documentation, 2 - UI Wireframes, 3 - Fix UX bugs, 3 - continue work on UI / CSS |  |  | 2 | 3 |  |  | 1 | 3 - UI / CSS Implementation, 3 - Fix UX bugs | 8
8 | Gloria | 11 | 10 | 1 | 3 - UI / CSS Implementation, 3 - Fix UX bugs |  |  |  | 10 |  |  |  | 3 - Refactor CSS, 6 - SDD document, 2 - Design Survey View for Survey Taker, 3 - Implementation of View Survey | 8
9 | Gloria | 11 | 10 | 1 | 3 - Refactor CSS, 6 - SDD document, 2 - Design Survey View for Survey Taker, 3 - Implementation of View Survey |  |  | 2 | 4 |  |  | 4 | 3 - Implementation of Survey Taker Views | 7
10 | Gloria | 8 | 7 | 1 | 3 - Implementation of Survey Taker Views, 3 - Fix UX bugs, 3 - Create Thank You page, 3 - Update Footer and Homepage About Section |  |  |  | 7 |  |  |  | 4 - Browser testing, 3 - Add Contact Us page content, 3 - finish About section on Homepage, 3 - Reports UI, 3 - UX bugs, 6 - Create final presentation deck | 20* (*for 2 weeks)

## Beth
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Beth | 6 | 5 | 1 | 0 - Learned tools, researched similar projects online 1 - Created system requirements based on discussions; updated SPMP | 2 | 3 | [5 empty] | Revise SPMP, help prepare for presentation, get more familiar with tools, create user stories for pivotaltracker | 10 hrs
2 | Beth | 8 | 7 | 1 | 1 - Wrote user stories, incorporated all user stories into requirements design in SPMP 2 - Created preliminary database design | 0 | 3 | 4 |  |  |  |  | Revise SPMP, learn how to create database in Yii, update SPMP with non-functional requirements | 8 hrs
3 | Beth | 8 | 7 | 1 | 0 - learning more about yii and migrations 1 - wrote non-functional requirements 2 - wrote DDL for yii migration | 3 | 1 | 3 |  |  |  |  | Revise SPMP to add minimum requirements; create yii migration for remainder of database | 6 hrs
4 | Beth | 8 | 7 | 1 | 0 - learning more about yii, Github and SourceTree 1 - improved database design and did yii migration 2 - wrote minimum requirements, clarified some areas of SPMP | 6 | 1 | 2 |  |  |  |  | Prepare design section of presentation; update database design | 8 hrs
5 | Beth | 6 | 5 | 1 | 1 - prepared for presentation 2 - updated database design; did sample migration |  | 5 | [5 empty] | Document code with PHPDoc | 8 hrs
6 | Beth | 7 | 6 | 1 | 0 - learning PHPDoc and learned more about migrations 3 - created migrations to eliminate foreign key issues | 4 | 2 | [5 empty] | Install tools for PHPUnit and learn tool Create standards for PHPDoc Update SPMP with revised user stories | 8 hrs
7 | Beth | 5 | 4 | 1 | 0 - researched PHPDocumenter 1 - designed documentation guidelines | 2 | 2 | [5 empty] | prepare for presentation Update SPMP with revised user stories document programs | 8 hrs
8 | Beth | 8 | 7 | 1 | 0 - learned code, Selenium server 3 - code review and documentation 6 - prepared for presentation | 2 |  |  | 2 |  |  | 3 | more documenting code work on SDD functional test use cases | 8 hrs
9 | Beth | 10 | 9 | 1 | 0 - code review 2 - worked on SDD 3 - tried to implement PHPUnit, Selenium Server 4 - reviewed functional test cases, some testing | 2 |  | 3 | 4 |  |  |  | work on reports with Fliden and Chao-Te | 8 hrs
10 | Beth | 8 | 7 | 1 | 2 - worked on software architecture diagram, outline for presentation |  |  | 7 |  |  |  |  | document code, work on reports with Fliden | 8 hrs

## Imaad
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Imaad | 5 | 4 | 1 | 0 - Installing github and MAMP server 0 - git and yii tutorials | 4 | [6 empty] | 1. Add Use cases 2. Empty commit on git 3. Work on the SPMP document 4. Learn yii framework | 7
2 | Imaad | 4.5 | 3.5 | 1 | 1 - Pivotal tracker user stories 0 - Git tutorial 0 - Empty commit on git 0 - review SPMP document and slide notes | 2.5 | 1 | [5 empty] | 1. Give feedback on database design 2. Complete coding initial registration and login pages with Vincent 3. Review yii framework naming conventions | 10
3 | Imaad | 8 | 7 | 1 | 0 - read up yii naming conventions 3 - Set up database 3 - Implement registration page and help integrate with Vincent's login page | 0.5 |  |  | 6.5 |  |  |  | 1. Complete yii migration 2. learn MVC yii model 3. convert last weeks code to integrate into the yii framewirk | 10
4 | Imaad | 8 | 7 | 1 | 3 - ran yii migration 0 - read up on the yii tutorial 3 - Helped with the integration of last weeks code into the yii framework | 2 |  |  | 5 |  |  |  | 1. Complete unti testing for one database table | 8
5 | Imaad | 10 | 9 | 1 | 0 - php unit, yii testing tutorials and documentation 3 - Install php unit 4 - unit test Survey table | 3 |  |  | 1 | 5 |  |  | 1. Merge unit testing to master 2. php documentation 3. Add more question types to the app 4. Fix current bugs found and unit test again | 10
6 | Imaad | 6 | 5 | 1 | 3 - Try implementing MC Questions 3 - Add home link when click on logo |  |  |  | 5 |  |  |  | 1. Implement multiple choice questions 2. Document unit test code | 10
7 | Imaad | 7 | 6 | 1 | 3 - Multiple choice implementation and fixes |  |  |  | 6 |  |  |  | 1. Prepare for presentation 2. Account Settings page 3. Integrate MCQ into dev | 12
8 | Imaad | 10 | 9 | 1 | 3 - Finished Multiple choice implementation 6 - Prepared for presentation |  |  |  | 6 |  |  | 3 | 1. Start Implementing survey/take render a survey form from the database | 10
9 | Imaad | 11 | 10 | 1 | 3 - Partial implementation of survey/take |  |  |  | 10 |  |  |  | 1. Finish implementing survey/take | 12
10 | Imaad | 12 | 11 | 1 | 3 - Completed take survey, along with authentication for taking and cookie authetication |  |  |  | 11 |  |  |  | 1. Help Gloria with contact page 2. Work on reports | 12

## Samuel
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Samuel | 5 | 5 | 1 | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion 5 - communication / management | 3 | 1 |  |  |  | 1 |  | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion & documentation 5 - communication / management
2 | Samuel | 4 | 4 | 1 | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion (update user story in PivotalTracker) 5 - communication / management | 1 | 2 |  |  |  | 1 |  | 0 - learning yii framework 0 - learning php 1 - RA discussion & documentation 4 - Test case design 5 - communication / management
3 | Samuel | 5 | 5 | 1 | 0 - learning yii framework 1 - RA discussion (update user story in PivotalTracker) 4 - Test case design 5 - communication / management | 1 | 1 |  |  | 2 | 1 |  | 0 - learning yii framework 0 - learning php 3 - data migration 4 - Test case design 4 - Unit test tool research 5 - communication / management
4 | Samuel | 4 | 4 | 1 | 0 - learning yii framework 4 - Test case design 5 - communication / management | 2 |  |  |  | 1 | 1 |  | 0 - learning yii framework 0 - learning php 3 - development env preparation 4 - Test case design 4 - Unit test tool research 5 - communication / management
5 | Samuel | 7 | 7 | 1 | 0 - learning yii framework 0 - learning php 3 - Unit Test implementation 4 - Test case design 4 - Unit test tool research 5 - communication / management | 2 | 1 |  | 3 | 0 | 1
6 | Samuel | 3 | 3 | 1 | 4 - Test case design 5 - communication / management |  |  |  |  | 2 | 1
7 | Samuel | 5 | 5 | 1 | 4 - Test case design 4 - Functional test (using selenium) 5 - communication / management |  |  |  |  | 4 | 1
8 | Samuel | 3 | 3 | 0 | 4 - Test case design 4 - Functional test documentation (using selenium) 5 - communication (mail) |  |  |  |  | 2 | 1
9 | Samuel | 5 | 5 | 1 | 4 - Test case design 4 - Functional test documentation (using selenium) 4 - Functional test 5 - communication (mail) |  |  |  |  | 4 | 1
10 | Samuel | 2 | 2 | 1 | 4 - Functional test documentation (using selenium) 5 - communication (mail) |  |  |  |  | 1 | 1

## Chao-Te
week # | Name | Total actual time | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | Type 0 | Type 1 | Type 2 | Type 3 | Type 4 | Type 5 | Type 6 | EST. tasks for next week | Total EST. time
1 | Chao-Te | 5 | 4 | 1 | 0 - Setup github and XAMPP server 0 - Review and learn PHP | 4 | [6 empty] | Learn more about YII framework and php Learn more about Git Create user stories | 8
2 | Chao-Te | 5 | 4 | 1 | 0 - Review and learn PHP 1 - Add user stories 1 - Review SPMP document | 3.5 | 1.5 | [5 empty] | Work on login page(back-end) with Imaad and Vincent Do research on SQL injection Understand database design | 8
3 | Chao-Te | 10 | 9 | 1 | 0 - Review and learn PHP 3 - User registration page 3 - Yii framework PHP code migration 4 - Test user registration page | 4 |  |  | 4 | 1 |  |  | Implement back-end functionalities with Imaad and Vincent Do research on SQL injection using Yii Code migration and test feature branch | 12
4 | Chao-Te | 10 | 9 | 1 | 0 - Read Yii APIs 3 - PHP code integration with Yii | 6 |  |  | 3 |  |  |  | Unit test for survey_response table Read tutorial on unit test using Yii Understand Yii APIs | 12
5 | Chao-Te | 11 | 10 | 1 | 0 - Setup and understand PHPUnit 3 - Implement unit test for SurveyResponse model 4 - Tested database CRUD function for existing models | 5 |  |  | 4 | 1 |  |  | Do more unit test, more test cases Understand 'Selenium Server' Generate php doc for existing implementation | 12
6 | Chao-Te | 6 | 5 | 1 | 0 - Learn Selenium server. Setup Selenium server 0 - Learn PHPDocumentor | 5 | [6 empty] | Learn functional test with Yii Implement functional test using selenium Generate php doc using PHPDocumentor | 10
7 | Chao-Te | 8.5 | 7.5 | 1 | 0 - Setup selenium server and plugins 3 - Implemented test scripts for user login/logout 4 - Simulate user behavior programmatically with Selenium | 2 |  |  | 5 | 0.5 |  |  | Prepare presentation material Add more functional tests | 10
8 | Chao-Te | 10 | 9 | 1 | 3 - Functional test (LoginTest, SignUpTest, SurveyTest) 4 - Setup Selenium and run the above test cases for our latest UI 5 - Discussed about the presentation |  |  |  | 6.5 | 2 | 0.5 |  | Create functional test case doc More Selenium test cases for latest UI Work with Vincent and Imaad (user report or create user survey) | 10
9 | Chao-Te | 9 | 7 | 1 | 0 - Generate charts and reports in Yii 4 - New test case document 5 - Document for Selenium setup, integration, and sample code | 2 |  |  |  | 2.5 | 3.5 |  | Create new branch - Report Implement report page Add more test cases | 10
10 | Chao-Te | 10 | 9 | 1 | 0 - Display interactive charts using Yii 3 - Reports view, added Yii plugin for charts 3 - Controller for reports (in SiteController) |  |  |  | 7 |  |  |  | Finish report page Work on testing document Prepare for presentation | 10