## Fliden
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Fliden | 7 | 6 | 1 | 0 - Reading about YII framework 1 - Review the requiremnts and features discussed in meeting 5 - Plan next meeting, communicate dates and tasks with the team 6 - Set up working environtment, install Netbeand, set up git, install XAMPP | 1 | 1 | 0 | 0 | 0 | 2 | 2 | - Complete Requirements Document - Plan next meeting - Write use stories in Pivotal tracker - Prepare presentation - Communicate with team to make sure we address all the weekly group tasks - Read more about YII framework | 10
2 | Fliden | 8 | 7 | 1 | 1 - Write user stories 1 - Write SPMP 5 - Plan next phase and iteration 5 - Plan next meeting, communicate dates and tasks with the team 6 - Write presentation bullets | 0 | 4 | 0 | 0 | 0 | 2 | 1 | - Complete Requirements Document with Risk Management - Review initial database design - Review YII framework, use it to create CRUD database operations - Try and implement YII MVC structure (create initial prototype) - Plan next meeting | 10
3 | Fliden | 9 | 8 | 1 | 0 - Lear and try Gii tool to generate code. 0 - Learn more about YII MVC structure 1 - Complete Requirements Document with Risk Management 1 - Pivotal Tracker update user stories and organization 2 - Review initial database design 3 - Set up and try the Yii db migration 5 - Plan next meeting and next week | 3 | 2 | 1 | 1 | 0 | 1 | 0 | - Address notes on SPMP - Pivotal Tracker: Add different tasks to user stories - Pivotal Tracker: Add UI to them etc - Pivotal Tracker: Split stories in smaller ones - Run Gii on all db tables to generate CRUD code - program create survey page and its related code and classes | 10
4 | Fliden | 8 | 7 | 1 | 1 - Update SPMP document 3 - Create CRUD operations for each db table 3 - Start programing create survey pages and its related classes and code 4 - Update Pivotal Tracker: add tasks, add/change person responsible for each task 4 - Communicate with the team 4 - Help other team members with version control/Yii framework | 0 | 1 | 0 | 5 | 0 | 1 | 0 | - Finish survey create page and its related code - Prepare and coordinate for next weeks presentation - Cooperate with Fyodor with certain changes to the code (remove user levels, add survey title field) - Cooperate with Gloria and Beth on the class diagram - try to create a few unit tests | 10
5 | Fliden | 15 | 14 | 1 | 3 - Finished survey create page and its related code 3 - Cooperate with Fyodor with certain changes to the code (remove user levels, add survey title field) 5 - Prepare and coordinate for next weeks presentation 5 - Help the team fix version control issues and Yii framework issues 5 - Plan next iteration/Add user stories/Change user story evaluations | 0 | 0 | 0 | 10 | 0 | 4 | 0 | - Coding of different type of questions - Write unit tests - Research phpdoc and plan documentation | 7
6 | Fliden | 5 | 4 | 0 | 1 - research phpdoc 3 - started coding of different type of questions 3 - write unit tests fpr remaining modules 3 - start writting docblocks | 1 | 0 | 0 | 4 | 0 | 0 | 0 | - finish writting phpdocs - continue coding different types of questions - plan next meeting and plan next presentation - finish and write report on unit testing - fix different bugs | 10

## Fyodor
week | Total time spent working this week (h) | Work time spent individually | Total meeting time | Time Spent on individual task (hrs) | [6 empty] | Estimated tasks for next week | Total estimated time
|  |  |  | Learning | Requirement Analysis | design | implementation | test | communication / management | unclassified
1 | 5 | 4 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 3 | 5
2 | 3.5 | 3.5 | 0 | 0 | 1 | 1 | 0.5 | 0 | 1 | 0 | 4 | 5
3 | 9 | 8 | 1 | 1 | 0 | 0 | 5 | 0 | 1 | 1 | 6 | 8
4 | 9 | 8 | 1 | 0 | 0 | 2 | 3 | 1 | 2 | 0 | 7 | 9
5 | 9 | 8 | 1 | 1 | 0 | 1 | 3 | 0 | 2 | 1 | 6 | 8
6 | 8 | 7 | 1 | 0 | 0 | 1 | 4 | 0 | 2 | 0 | 8 | 9
7 | 0 | 0
8 | 0 | 0
9 | 0 | 0
10 | 0 | 0
11 | 0 | 0
12 | 0 | 0
Note on G2: Read through the document Beth sent around and provided feedback.
Note on I2: Configured Github repo for the team and added the yii bootstrap for quick and easy startup
Note on K2: wrote up a brief tutorial on how to get set up with Github and the project that has been commited.
Note on L2: Helped Beth configure her WAMP installation.
Note on G3: Read through requirements and made sure things are correct.
Note on H3: Created a ERM to double check team logic on FK use and inheritense
Note on I3: Updated Documentation. Filed issue with ignore file.
Note on K3: Talked about ERM that Beth sent around. Adding professor to Github and email/username resolution.
Note on F4: migration review.
Note on I4: * Moved the config passwords outside the config file. * Themes set up to be used. * Ignored environment specific configuration files. * Removed redundant layout * Created parent Model class* * Added survey_creater table to database migration * Generated survey_creator model * Authentication is done against the database test user.
Note on K4: helping set up and explaining migrations and how to use yiic to run them.
Note on L4: Helped beth configure her MySQL database.
Note on H5: Worked on Gloria's design and integrated it with master..
Note on I5: * Worked on CRUD operations and fixed up the * Authentication/Registration module. * Issue fixes.
Note on J5: Manual navigation and authentication/registration work properly.
Note on K5: * Emailing group of major updates. * Pivitol tracker finishing tasks. * Video chat with Gloria to set up her MAMP
Note on F6: figuring out how to remove FK'd column in a migration. 1)remove FK, 2)remove index, 3) remove column.
Note on I6: * Commenting * Cleaning up code & removing uneeded files. * Minor Design fixes * Bug fixes * Migration additions.
Note on K6: * Communicated with Dloria about design specifics and how to accomplish some tasks. * Taught team members how to work with Yii. * Discussed with Beth various strategies on how to clean up the schema.
Note on L6: code review.
Note on H7: styles the draggable questions so they can be ordered.
Note on I7: Questions are now sortable for a survey.
Note on K7: updating issues on Github. Assigning issue on Github Reviewing code.

## Chih-Chi
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Chih-Chi | 5 | 4 | 1 | 0 - Setup and learn Github 0 - Read on Yii frame work 0 - Install wamp server | 4 | [6 empty] | Add user story on PivotalTracker Make sure Github is working Help complete our SPMP document Read more on Yii framework | 6
2 | Chih-Chi | 6 | 5 | 1 | 2 - add user storys on PivitalTracker 0 - Git tutorial lesson 0 - Read through SPMP document 0 - Make a commit on GitHub | 4 |  | 1 |  |  |  |  | Work on login and registor page Read more on Yii framework Understand and provide feedback to our database design | 8
3 | Chih-Chi | 9 | 8 | 1 | 3 - Login page and integrating 3 - Yii database migration |  |  |  | 8 |  |  |  | Port login page to Yii framework | 10
4 | Chih-Chi | 11 | 10 | 1 | 3 - Login/Register page and Yii framework intergration |  |  |  | 10 |  |  |  | Prepare for next weeks report Unit testing | 6
5 | Chih-Chi | 6.5 | 5.5 | 1 | 0 - learning phpunit and unit testing 3 - unit test case for survey creator model 6 - presentation preparation | 4 |  |  | 1 |  |  | 0.5 | Help with implementing more survey question types More unit testing Learn php doc | 9
6 | Chih-Chi | 6 | 5 | 1 | 0 - learning php documentor | 5
7 | Chih-Chi | 0 | 0
8 | Chih-Chi | 0 | 0

## Gloria
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Gloria | 5 | 4 | 1 | 0 - Learn GitHub & Yii Framework 0 - Set up Tools | 4 | [6 empty] | 1 - Write User Stories, 1 - Review Requirements Doc, 2 - Design project logo, 2 - Start Wireframes, 6 - Create presentation doc for Group Presentation | 8
2 | Gloria | 9 | 8 | 1 | 1 - Write User Stories, 1 - Review Requirements Doc, 2 - Design project logo, 2 - Create user flow, 6 - Create presentation doc for Group Presentation |  | 2 | 4 |  |  |  | 2 | 2 - Wireframes | 6
3 | Gloria | 8 | 7 | 1 | 2 - Wireframes, 2 - Class Diagram |  |  | 7 |  |  |  |  | 0 - Learn & set up Yii, 3 - CSS, 2 - Wireframes | 7
4 | Gloria | 11 | 10 | 1 | 1 - Update SPMP doc based on feedback, 1 - add new User Story, 2 - Add wireframes to Pivotal Tracker, 0 - Learn Yii, 0 - Set up local database, 3 - Homepage, Survey & Survey Editor pages UI (PHP & CSS) | 4 | 1 | 1 | 4 |  |  |  | 3 - Finish UI for iteration #1, 2 - Work on look & feel, 6 - Presentation deck for Group Presentation | 8
5 | Gloria | 12 | 11 | 1 | 2 - Work on look & feel, 3 - Finish UI for iteration #1, 6 - Presentation deck for Group Presentation |  |  | 1 | 6 |  |  | 4 | 6 - PHP Documentation, 3 - Continue working on UI, 3 - Adding more questions | 5
6 | Gloria | 5 | 4 | 1 | 3 - UI for adding more question types, 6 - PHP Documentation |  |  |  | 3 |  |  | 1 | 6 - PHP Documentation, 2 - UI Wireframes, 3 - Fix UX bugs, 3 - continue work on UI / CSS | 7

## Beth
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Beth | 6 | 6 | 1 | 0 - Learned tools, researched similar projects online 1 - Created system requirements based on discussions; updated SPMP | 2 | 3 | [5 empty] | Revise SPMP, help prepare for presentation, get more familiar with tools, create user stories for pivotaltracker | 10 hrs
2 | Beth | 8 | 8 | 1 | 1 - Wrote user stories, incorporated all user stories into requirements design in SPMP 2 - Created preliminary database design | 0 | 3 | 4 |  |  |  |  | Revise SPMP, learn how to create database in Yii, update SPMP with non-functional requirements | 8 hrs
3 | Beth | 8 | 8 | 1 | 0 - learning more about yii and migrations 1 - wrote non-functional requirements 2 - wrote DDL for yii migration | 3 | 1 | 3 |  |  |  |  | Revise SPMP to add minimum requirements; create yii migration for remainder of database | 6 hrs
4 | Beth | 8 | 8 | 1 | 0 - learning more about yii, Github and SourceTree 1 - improved database design and did yii migration 2 - wrote minimum requirements, clarified some areas of SPMP | 6 | 1 | 2 |  |  |  |  | Prepare design section of presentation; update database design | 8 hrs
5 | Beth | 6 | 6 | 1 | 1 - prepared for presentation 2 - updated database design; did sample migration |  | 5 | [5 empty] | Document code with PHPDoc | 8 hrs
6 | Beth | 7 | 6 | 1 | 0 - learning PHPDoc and learned more about migrations 3 - created migrations to eliminate foreign key issues | 4 | 2 | [5 empty] | Install tools for PHPUnit and learn tool Create standards for PHPDoc Update SPMP with revised user stories | 8 hrs

## Imaad
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Imaad | 5 | 4 | 1 | 0 - Installing github and MAMP server 0 - git and yii tutorials | 4 | [6 empty] | 1. Add Use cases 2. Empty commit on git 3. Work on the SPMP document 4. Learn yii framework | 7
2 | Imaad | 4.5 | 3.5 | 1 | 1 - Pivotal tracker user stories 0 - Git tutorial 0 - Empty commit on git 0 - review SPMP document and slide notes | 2.5 | 1 | [5 empty] | 1. Give feedback on database design 2. Complete coding initial registration and login pages with Vincent 3. Review yii framework naming conventions | 10
3 | Imaad | 8 | 7 | 1 | 0 - read up yii naming conventions 3 - Set up database 3 - Implement registration page and help integrate with Vincent's login page | 0.5 |  |  | 6.5 |  |  |  | 1. Complete yii migration 2. learn MVC yii model 3. convert last weeks code to integrate into the yii framewirk | 10
4 | Imaad | 8 | 7 | 1 | 3 - ran yii migration 0 - read up on the yii tutorial 3 - Helped with the integration of last weeks code into the yii framework | 2 |  |  | 5 |  |  |  | 1. Complete unti testing for one database table | 8
5 | Imaad | 10 | 9 | 1 | 0 - php unit, yii testing tutorials and documentation 3 - Install php unit 4 - unit test Survey table | 3 |  |  | 1 | 5 |  |  | 1. Merge unit testing to master 2. php documentation 3. Add more question types to the app 4. Fix current bugs found and unit test again | 10
6 | Imaad | 6 | 5 | 1 | 3 - Try implementing MC Questions 3 - Add home link when click on logo |  |  |  | 3 |  |  |  | 1. Implement multiple choice questions 2. Document unit test code | 10

## Samuel
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Samuel | 5 | 5 | 1 | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion 5 - communication / management | 3 | 1 |  |  |  | 1 |  | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion & documentation 5 - communication / management
2 | Samuel | 4 | 4 | 1 | 0 - learning yii framework 0 - learning environment setup (wamp) 0 - learning github 1 - RA discussion (update user story in PivotalTracker) 5 - communication / management | 1 | 2 |  |  |  | 1 |  | 0 - learning yii framework 0 - learning php 1 - RA discussion & documentation 4 - Test case design 5 - communication / management
3 | Samuel | 5 | 5 | 1 | 0 - learning yii framework 1 - RA discussion (update user story in PivotalTracker) 4 - Test case design 5 - communication / management | 1 | 1 |  |  | 2 | 1 |  | 0 - learning yii framework 0 - learning php 3 - data migration 4 - Test case design 4 - Unit test tool research 5 - communication / management
4 | Samuel | 4 | 4 | 1 | 0 - learning yii framework 4 - Test case design 5 - communication / management | 2 |  |  |  | 1 | 1 |  | 0 - learning yii framework 0 - learning php 3 - development env preparation 4 - Test case design 4 - Unit test tool research 5 - communication / management
5 | Samuel | 7 | 7 | 1 | 0 - learning yii framework 0 - learning php 3 - Unit Test implementation 4 - Test case design 4 - Unit test tool research 5 - communication / management | 2 | 1 |  | 3 | 0 | 1
6 | Samuel | 3 | 3 | 1 | 4 - Test case design 5 - communication / management |  |  |  |  | 2 | 1
7 | Samuel
8 | Samuel
9 | Samuel
10 | Samuel

## Chao-Te
week # | Name | Total actual time | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | Type 0 | Type 1 | Type 2 | Type 3 | Type 4 | Type 5 | Type 6 | EST. tasks for next week | Total EST. time
1 | Chao-Te | 5 | 4 | 1 | 0 - Setup github and XAMPP server 0 - Review and learn PHP | Type 0: 4 | Learn more about YII framework and php Learn more about Git Create user stories | 8
2 | Chao-Te | 5 | 4 | 1 | 0 - Review and learn PHP 1 - Add user stories 1 - Review SPMP document | Type 0: 3.5; Type 1: 1.5 | Work on login page(back-end) with Imaad and Vincent Do research on SQL injection Understand database design | 8
3 | Chao-Te | 10 | 9 | 1 | 0 - Review and learn PHP 3 - User registration page 3 - Yii framework PHP code migration 4 - Test user registration page | Type 0: 4; Type 3: 4; Type 4: 1 | Implement back-end functionalities with Imaad and Vincent Do research on SQL injection using Yii Code migration and test feature branch | 12
4 | Chao-Te | 10 | 9 | 1 | 0 - Read Yii APIs 3 - PHP code integration with Yii | Type 0: 6; Type 3: 3 | Unit test for survey_response table Read tutorial on unit test using Yii Understand Yii APIs | 12
5 | Chao-Te | 11 | 10 | 1 | 0 - Setup and understand PHPUnit 3 - Implement unit test for SurveyResponse model 4 - Tested database CRUD function for existing models | Type 0: 5; Type 3: 4; Type 4: 1 | Do more unit test, more test cases Understand 'Selenium Server' Generate php doc for existing implementation | 12
6 | Chao-Te | 6 | 5 | 1 | 0 - Learn Selenium server. Setup Selenium server 0 - Learn PHPDocumentor | Type 0: 5 | Learn functional test with Yii Implement functional test using selenium Generate php doc using PHPDocumentor | 10